# 📘 DOCUMENT 3

# Phase 2 Secondary Services Roadmap & Expansion Strategy

## Hawassa MESOB One-Stop Service Center

Prepared For:
H.E. Mayor Tiratu Beyene
Hawassa City Administration

Prepared By:
Chief Enterprise Architect & Lead Consultant
Hawassa MESOB One-Stop Service Program

# PART 1

(Sections 1–4: Strategic Purpose, Phase 2 Design Principles, Service Expansion Domains, Detailed Service List)

# 1. EXECUTIVE PURPOSE OF PHASE 2

## 1.1 Why Phase 2 Exists

Phase 1 stabilizes:

- Revenue

- High-volume services

- Public trust

- Integration discipline

Phase 2 expands MESOB into:

- Urban governance digitization

- Infrastructure permitting

- Social services digitization

- Compliance monitoring

- Inter-agency intelligence sharing

Phase 2 is not “more services.”

It is system maturity.

## 1.2 Strategic Objectives of Phase 2

Phase 2 must achieve:

- Deep institutional integration

- GIS-enabled urban control

- Automated cross-bureau workflows

- Predictive governance dashboards

- Reduced regulatory bottlenecks

- Strengthened enforcement capability

## 1.3 Timing

Phase 2 should begin:

6–9 months after Phase 1 stabilization.

Prerequisites:

- SLA compliance above 80%

- Core API endpoints operational

- Revenue dashboard active

- Bureau readiness verified

# 2. PHASE 2 DESIGN PRINCIPLES

Phase 2 services must meet at least 3 of the following criteria:

- Cross-bureau dependency

- Infrastructure or zoning impact

- Public compliance enforcement

- Regulatory approval complexity

- High complaint frequency

- Strategic economic impact

Phase 2 builds on the digital backbone established in Phase 1.

# 3. PHASE 2 SERVICE DOMAINS

Phase 2 expands MESOB into:

- Construction & Urban Planning Services

- Infrastructure & Utilities Coordination

- Environmental & Sanitation Regulation

- Public Safety & Compliance

- Civil Registration Enhancements

- Social Protection Services

- Digital Governance & Transparency Tools

Estimated Total Services: 35–45

# 4. DETAILED PHASE 2 SERVICE BREAKDOWN

# 4.1 CONSTRUCTION & URBAN PLANNING SERVICES

(12–15 Services)

These services require GIS integration and multi-department review.

## 4.1.1 Building Permit Application

Current challenge:

- Multi-office physical approvals

- Long delays

- Lack of transparency

Phase 2 Digital Model:

- Digital architectural submission

- Zoning compliance auto-check

- Engineering review workflow

- Fee calculation engine

- Approval issuance

Requires:

- Zoning GIS layer

- Structural compliance module

- Environmental clearance check

SLA Target: 15 working days

## 4.1.2 Construction Stage Inspection Scheduling

Allows digital scheduling of inspection visits.

Reduces:

- Informal coordination

- Delay manipulation

## 4.1.3 Occupancy Certificate Issuance

Requires:

- Completion inspection validation

- Tax compliance check

- Infrastructure connection verification

## 4.1.4 Building Plan Amendment Approval

For modification requests.

Requires version control tracking.

## 4.1.5 Demolition Permit

Includes:

- Safety compliance verification

- Waste disposal plan submission

## 4.1.6 Zoning Change Application

Complex regulatory service.

Requires:

- GIS zoning map integration

- Public notice workflow

- Review committee approval module

## 4.1.7 Infrastructure Impact Assessment Filing

Required for large projects.

## 4.1.8 Utility Connection Approval (Preliminary)

Coordination with:

- Water authority

- Electricity provider

- Telecom provider

## 4.1.9 Road Access Permit

## 4.1.10 Outdoor Advertising Permit

High revenue potential.

## 4.1.11 Signage Permit

## 4.1.12 Fence Construction Approval

# 4.2 INFRASTRUCTURE & UTILITIES SERVICES

(6–8 Services)

## 4.2.1 Water Service Application Tracking

## 4.2.2 Sewerage Connection Permit

## 4.2.3 Electricity Connection Coordination Interface

(Not necessarily provided by MESOB but tracked)

## 4.2.4 Telecom Infrastructure Installation Permit

## 4.2.5 Road Excavation Permit

## 4.2.6 Utility Relocation Request

# 4.3 ENVIRONMENTAL & SANITATION SERVICES

(5–7 Services)

## 4.3.1 Environmental Compliance Certificate

## 4.3.2 Waste Management Registration

## 4.3.3 Industrial Pollution Reporting

## 4.3.4 Noise Permit Issuance

## 4.3.5 Solid Waste Contractor Licensing

# 4.4 PUBLIC SAFETY & COMPLIANCE SERVICES

(5–6 Services)

## 4.4.1 Fire Safety Certification

## 4.4.2 Public Event Permit

## 4.4.3 Crowd Management Approval

## 4.4.4 Emergency Compliance Reporting

# 4.5 CIVIL REGISTRATION ENHANCEMENTS

(Selective Integration)

## 4.5.1 Residence Confirmation Letter

## 4.5.2 Civil Record Verification for Land/Business

Integrated via API to federal civil registry where permitted.

# 4.6 SOCIAL PROTECTION SERVICES

## 4.6.1 Youth Employment Registration

## 4.6.2 Women Enterprise Support Registration

## 4.6.3 Urban Safety Net Program Enrollment

# 4.7 DIGITAL GOVERNANCE & TRANSPARENCY TOOLS

## 4.7.1 Public Service Status Tracking Portal

## 4.7.2 Online Complaint Management Dashboard

## 4.7.3 Executive Performance Dashboard (Mayor View)

# PHASE 2 SERVICE COUNT SUMMARY

| Domain | Estimated Services |
| --- | --- |
| Construction & Planning | 12 |
| Infrastructure & Utilities | 6 |
| Environmental | 5 |
| Public Safety | 5 |
| Civil Registration | 2 |
| Social Protection | 3 |
| Governance Tools | 3 |

Total Estimated Phase 2 Services: 36

# STRATEGIC IMPACT OF PHASE 2

Phase 2 enables:

- Full urban control visibility

- GIS-based decision support

- Infrastructure coordination discipline

- Digital enforcement capability

- Reduced corruption risk

- Increased investment confidence

# END OF DOCUMENT 3 – PART 1

This part covered:

✔ Strategic purpose
✔ Design principles
✔ Domain expansion
✔ Detailed service listing

Reply with:

“Proceed with Document 3, Part 2.”

Next we will produce:

Operational integration model
Technical prerequisites
Phased rollout timeline
Budget & capacity implications
Risk controls for Phase 2 expansion.

# 📘 DOCUMENT 3

# Phase 2 Secondary Services Roadmap & Expansion Strategy

## Hawassa MESOB One-Stop Service Center

PART 2
(Sections 5–9: Operational Integration Model, Technical Prerequisites, Rollout Timeline, Budget Implications, Risk & Governance Controls)

# 5. PHASE 2 OPERATIONAL INTEGRATION MODEL

Phase 2 introduces complex, multi-bureau workflows.

Unlike Phase 1 (mostly transactional services), Phase 2 services are:

- Multi-stage

- Multi-review

- GIS-dependent

- Regulatory-heavy

Therefore, an advanced integration model is required.

## 5.1 Multi-Bureau Workflow Architecture

Each Phase 2 service must follow:

- Digital Submission Layer (MESOB front desk or portal)

- Automated Routing Engine

- Bureau Review Modules

- Cross-Bureau Validation APIs

- Decision Consolidation Engine

- Digital Approval / Rejection Issuance

- SLA Monitoring & Escalation

Example: Building Permit

Applicant → MESOB → Urban Planning → Engineering → Environmental → Revenue → Final Approval

Each step logged digitally.

## 5.2 SLA Enforcement Model

Phase 2 introduces:

- Internal SLA per bureau step

- Escalation rule after threshold breach

- Automatic notification to bureau head

- Escalation to Mayor dashboard if overdue beyond tolerance

## 5.3 Integration with National MESOB Mesh

Phase 2 services must integrate with:

- Federal land validation (where required)

- Civil registry verification

- Tax authority (if federal overlap exists)

Integration path:

Hawassa MESOB → National API Gateway → Federal System

Clear demarcation:

City services remain locally governed.

# 6. TECHNICAL PREREQUISITES FOR PHASE 2

Phase 2 cannot start unless the following are operational:

## 6.1 Stable API Endpoints (Phase 1 Proven)

Every Phase 1 bureau must have:

- Documented APIs

- Authentication mechanism

- Error logging

- Version control

If not, Phase 2 expansion will fail.

## 6.2 GIS Integration Platform

Construction & zoning services require:

- Digital zoning map

- Plot overlay capability

- Boundary validation

- Coordinate reference system alignment

Minimum requirement:

- GIS server deployment

- Data digitization of zoning layers

- API exposure for compliance checking

## 6.3 Workflow Orchestration Engine

Needed for:

- Multi-step approvals

- Parallel review processing

- Escalation rules

- Conditional routing

Must support:

- Audit trail

- Time stamping

- Digital signature integration

## 6.4 Document Management System (DMS)

Phase 2 requires:

- Version control for building plans

- Large file storage

- Secure document access

- Retention policy enforcement

## 6.5 Increased Hosting Capacity

Compared to Phase 1:

- Larger storage

- Higher bandwidth

- Increased concurrency

- Disaster recovery readiness

If Ethio Telecom provides hosting:

Capacity requirements must be upgraded to Phase 2 load projections.

# 7. PHASE 2 ROLLOUT TIMELINE

## 7.1 Recommended Phased Approach

Phase 2 should not be launched all at once.

Recommended waves:

### Wave 2A (Months 7–12)

- Building Permit

- Occupancy Certificate

- Zoning Change

- Road Excavation Permit

- Environmental Compliance Certificate

### Wave 2B (Months 12–18)

- Utility Coordination

- Fire Safety Certification

- Public Event Permit

- Industrial Expansion Approval

- Waste Contractor Licensing

### Wave 2C (Months 18–24)

- Digital Governance Tools

- Executive Dashboards

- Social Protection Integrations

## 7.2 Milestone Targets

Month 6: Phase 1 SLA > 80%
Month 9: GIS baseline completed
Month 12: Wave 2A operational
Month 18: Wave 2B operational
Month 24: Full Phase 2 stabilization

# 8. BUDGET & CAPACITY IMPLICATIONS

Phase 2 cost drivers:

- GIS infrastructure

- Workflow engine licensing/development

- Storage expansion

- Training for technical review staff

- Inspection digitization tools

- Additional integration development

Estimated budget multiplier relative to Phase 1:

1.5x – 2x Phase 1 IT cost

However:

Operational efficiency gains offset long-term costs.

# 9. RISK & GOVERNANCE CONTROLS

Phase 2 risks are higher than Phase 1.

## 9.1 Technical Risks

- GIS data incompleteness

- API instability

- Overloaded hosting environment

- Workflow engine misconfiguration

Mitigation:

- Pre-implementation pilot

- Stress testing

- Data digitization audit

## 9.2 Institutional Risks

- Bureau resistance to digital review

- SLA non-compliance

- Manual parallel processing

- Informal bypass attempts

Mitigation:

- Mayoral directive enforcement

- SLA penalty mechanism

- Digital-only approval mandate

## 9.3 Legal & Regulatory Risks

- Zoning regulation conflicts

- Land record disputes

- Environmental law overlap

Mitigation:

- Legal harmonization review

- Regulatory compliance audit before launch

## 9.4 Financial Risks

- Underestimation of integration cost

- Vendor scope ambiguity

- Hosting cost escalation

Mitigation:

- Detailed BoQ (Document 8)

- Vendor scope clarification (Document 9)

- Capacity forecasting model

# PHASE 2 GOVERNANCE STRUCTURE

Recommended:

- Phase 2 Steering Committee chaired by Mayor

- Technical Subcommittee

- GIS Taskforce

- Integration Review Board

- SLA Compliance Monitoring Unit

# PHASE 2 SUCCESS METRICS

- Permit issuance time reduced by 40%

- Construction approval backlog reduced by 50%

- Utility coordination delays reduced by 60%

- Investor approval transparency improved

- Real-time urban planning dashboard operational

# DOCUMENT 3 COMPLETE

This concludes:

✔ Phase 2 Service Domains
✔ Integration Model
✔ Technical Prerequisites
✔ Rollout Timeline
✔ Budget Implications
✔ Risk & Governance Controls

Reply with:

“Proceed with Document 4, Part 1.”

Next we begin:

Infrastructure & Technology Needs
(Exact technology stack required to run Phase 1 priority services).