# 📘 DOCUMENT 5

# Stakeholder Mapping & Bureau Readiness Framework

## Hawassa MESOB One-Stop Service Center

Prepared For:
H.E. Mayor Tiratu Beyene
Hawassa City Administration

Prepared By:
Chief Enterprise Architect & Lead Consultant
Hawassa MESOB One-Stop Service Program

# PART 1

(Sections 1–4: Stakeholder Landscape, Governance Structure, Bureau Classification Model, Readiness Framework for Bureaus WITH Existing IT Systems)

# 1. STAKEHOLDER LANDSCAPE OVERVIEW

The MESOB One-Stop Service Center is not a single-organization project.

It is a city-wide transformation program involving:

- Executive leadership

- Technical implementers

- Service-owning bureaus

- Infrastructure providers

- National MESOB coordination body

- Financial institutions

- Citizens & businesses

Without structured stakeholder governance, integration failure is inevitable.

## 1.1 Primary Stakeholder Groups

### 1. Executive Leadership

- Hawassa City Mayor (Program Sponsor)

- City Cabinet

- Bureau Heads

Role:

- Political authority

- Policy enforcement

- SLA accountability

- Conflict resolution

### 2. MESOB Core Implementation Team

- Chief Enterprise Architect

- Program Manager

- Integration Lead

- Infrastructure Lead

- Legal & Compliance Advisor

- Finance Controller

Role:

- Design & coordination

- Technical validation

- Vendor supervision

- Progress reporting

### 3. Service-Owning Bureaus (Phase 1)

| Bureau | Primary Phase 1 Role |
| --- | --- |
| Land & Cadaster | Lease, title, valuation |
| Revenue Bureau | Tax & payments |
| Trade & Industry | Licensing |
| Investment Office | Project registration |
| Health Office | Clinic permits |
| Education Office | School permits |

### 4. Infrastructure Provider

Primary Candidate:
Ethio Telecom (subject to contract finalization)

Potential Scope:

- Hosting infrastructure

- Connectivity

- Queue management system

- Operational platform

Scope Clarification Required:

- API development responsibility

- Backend system creation (for bureaus without systems)

### 5. National MESOB Taskforce

Role:

- Federal alignment

- API Gateway/Mesh connectivity

- Inter-governmental standards

- Compliance validation

# 2. GOVERNANCE STRUCTURE FOR MESOB

## 2.1 Executive Steering Committee

Chair:
Mayor

Members:

- Bureau Heads

- Program Director

- ICT Representative

- Finance Representative

Responsibilities:

- Policy decisions

- Escalation resolution

- Budget approval

- Performance review

Meeting Frequency:
Monthly (during Phase 1)

## 2.2 Technical Steering Committee

Members:

- Enterprise Architect

- Integration Lead

- Vendor Technical Lead

- Bureau IT Heads

Responsibilities:

- API review

- Integration testing

- Infrastructure validation

- Change control approval

Meeting Frequency:
Bi-weekly

## 2.3 SLA Compliance Unit

Responsibilities:

- Monitor service performance

- Generate monthly reports

- Escalate SLA breaches

- Recommend corrective actions

Reports directly to Mayor’s Office.

# 3. BUREAU CLASSIFICATION MODEL

Critical distinction:

All bureaus fall into one of two categories.

## CATEGORY A

Bureaus WITH Existing IT Systems

Examples (subject to verification):

- Land Registry System

- Tax Collection System

- Business Licensing Database

Characteristics:

- Existing database

- Operational software

- Internal digital records

- Some level of automation

Risk:
Lack of API exposure.

## CATEGORY B

Bureaus WITHOUT IT Systems

Characteristics:

- Paper-based records

- Manual registers

- No structured database

- No API capability

Risk:
No integration readiness.

# 4. READINESS FRAMEWORK

## FOR BUREAUS WITH EXISTING IT SYSTEMS (CATEGORY A)

This section provides a structured checklist.

These bureaus must prepare for API integration.

## 4.1 Governance & Policy Readiness

Checklist:

□ Bureau head formally commits to digital integration
□ Data-sharing agreement signed
□ Legal clearance for API exposure granted
□ Internal digital transformation focal person appointed

## 4.2 Technical Readiness Checklist

Each Category A bureau must confirm:

□ Database structure documented
□ Data fields mapped
□ Data quality audit completed
□ Duplicate record assessment completed
□ Access control model defined
□ Backup system verified

## 4.3 API Exposure Requirements

Each bureau must:

□ Identify data endpoints required for MESOB
□ Define input & output fields
□ Approve REST-based API format
□ Support token-based authentication
□ Support encrypted communication

## 4.4 Minimum API Set Per Bureau

Example: Land Bureau

Must expose APIs for:

- Lease retrieval

- Ownership validation

- Arrears check

- Transfer update

- Certificate issuance confirmation

Example: Revenue Bureau

Must expose:

- Tax compliance check

- Payment posting

- Arrears calculation

- Revenue reconciliation status

## 4.5 Responsibility Matrix (Critical Issue)

Key Question:

Who builds the API wrapper?

Options:

Option 1:
Ethio Telecom builds API wrapper layer.

Option 2:
Bureau IT team builds APIs.

Option 3:
MESOB system vendor builds integration layer.

Recommendation:

The responsibility must be clearly stated in contract before implementation begins.

No bureau integration should start without signed responsibility matrix.

## 4.6 Testing & Validation Checklist

Before go-live:

□ API test environment available
□ API performance test completed
□ Security penetration test completed
□ Error-handling scenario validated
□ SLA timing validation tested

## 4.7 Risk if Category A Not Ready

- Manual parallel processing continues

- Digital approval delayed

- SLA failure

- Political backlash

- Revenue reconciliation gaps

# CATEGORY A SUMMARY

If bureau already has IT system:

Primary focus = API exposure & data cleaning.

Integration complexity = Medium.

Success depends on:

- Strong technical oversight

- Clear vendor responsibility

- Data governance discipline

# END OF DOCUMENT 5 – PART 1

Covered:

✔ Stakeholder landscape
✔ Governance structure
✔ Bureau classification model
✔ Full readiness checklist for bureaus WITH IT systems

Reply with:

“Proceed with Document 5, Part 2.”

Next we will produce:

✔ Readiness framework for bureaus WITHOUT IT systems
✔ API development responsibility model
✔ Capacity building requirements
✔ Institutional reform controls
✔ Enforcement & compliance model.

# 📘 DOCUMENT 5

# Stakeholder Mapping & Bureau Readiness Framework

## Hawassa MESOB One-Stop Service Center

PART 2
(Sections 5–9: Readiness Framework for Bureaus WITHOUT IT Systems, API Development Responsibility Model, Capacity Building, Institutional Controls, Enforcement & Compliance)

# 5. READINESS FRAMEWORK

## FOR BUREAUS WITHOUT EXISTING IT SYSTEMS (CATEGORY B)

These bureaus currently operate:

- Paper-based workflows

- Manual approval signatures

- Physical registers

- No digital database

- No integration capability

If these bureaus are not digitized properly, MESOB will become:

A digital front desk connected to manual back offices.

This must be avoided.

## 5.1 Category B Transformation Path

Each bureau without systems must undergo:

- Business Process Documentation

- Workflow Simplification

- Data Model Definition

- Basic Backend System Development

- API Endpoint Creation

- Staff Training

- Data Migration (if necessary)

## 5.2 Business Process Documentation Checklist

Before system development:

□ Current workflow mapped
□ Approval hierarchy defined
□ Required documents listed
□ Processing timeline documented
□ Bottlenecks identified
□ Legal compliance confirmed

## 5.3 Workflow Simplification Requirement

Do NOT digitize inefficient manual processes.

Before development:

- Remove unnecessary approval layers

- Eliminate redundant signatures

- Define clear SLA timelines

- Standardize forms

Only optimized workflows should be digitized.

## 5.4 Backend System Development Requirements

For each Category B bureau:

Minimum required:

- Structured relational database

- Service management interface

- Approval routing logic

- Document upload capability

- Audit logging

- User role management

System must be:

- API-ready

- Modular

- Scalable

## 5.5 API Endpoint Creation (Mandatory)

Even if backend system is simple,
it must expose structured APIs for MESOB.

Required endpoints:

- Record creation

- Record update

- Status retrieval

- Approval confirmation

- Document attachment

Without APIs, integration cannot function.

# 6. API DEVELOPMENT RESPONSIBILITY MODEL

This is the most critical governance decision.

Because:

Ethio Telecom may provide infrastructure and operational systems (queue, hosting),
but may not automatically develop bureau-specific backend systems.

This must be explicitly defined.

## 6.1 Three Possible Responsibility Models

### Model A: Ethio Telecom Full Stack Responsibility

Ethio Telecom provides:

- Hosting

- Core MESOB platform

- Backend systems for Category B bureaus

- API wrapper for Category A bureaus

- Integration layer

Advantage:
Single accountability.

Risk:
Vendor dependency & scope inflation.

### Model B: Split Responsibility Model

Ethio Telecom provides:

- Hosting

- Network

- Queue system

MESOB Application Vendor provides:

- Backend systems

- API layer

- Workflow engine

Advantage:
Specialized integration quality.

Risk:
Coordination complexity.

### Model C: Bureau-Driven API Development

Each bureau builds its own backend & APIs.

Risk:

- Inconsistent standards

- Delays

- Integration fragmentation

- Technical quality variation

Not recommended unless bureaus have strong IT teams.

## 6.2 Recommended Model for Hawassa

Given current context:

- Strong mayoral push

- Time-sensitive implementation

- Uneven IT capacity

Recommended:

Modified Model A with strict contract safeguards.

Meaning:

Ethio Telecom may act as infrastructure lead,
but:

Contract must clearly define:

- API development scope

- Backend system creation for Category B bureaus

- Ownership of source code

- Data ownership

- Exit/migration rights

# 7. CAPACITY BUILDING REQUIREMENTS

Technology alone is insufficient.

Institutional capacity must be built.

## 7.1 Technical Staff Training

For each bureau:

- API understanding

- Workflow monitoring

- Data entry discipline

- SLA tracking

- Basic system troubleshooting

## 7.2 MESOB Counter Staff Training

Must cover:

- Multi-service handling

- System navigation

- Payment reconciliation

- Citizen communication

- Escalation protocol

## 7.3 Executive Training

Mayor & Bureau Heads require:

- Dashboard interpretation

- SLA monitoring understanding

- Escalation procedure familiarity

- Data-driven decision use

# 8. INSTITUTIONAL CONTROL FRAMEWORK

MESOB must not operate in parallel with manual processes.

Policy must enforce:

“Digital-first and digital-only processing for Phase 1 services.”

## 8.1 Parallel Processing Prohibition

Once MESOB launches:

- No manual certificate issuance outside system

- No offline approval bypass

- No manual payment acceptance outside system

All transactions must be logged digitally.

## 8.2 SLA Enforcement Mechanism

Each service must have:

- Defined SLA timeline

- Automatic timer

- Escalation notification

- Performance reporting

Repeated SLA breach must trigger:

- Administrative review

- Performance warning

## 8.3 Performance Accountability Model

Monthly dashboard must show:

- Bureau SLA compliance rate

- Pending cases

- Revenue generated

- Escalation cases

Mayor reviews monthly.

# 9. ENFORCEMENT & COMPLIANCE MODEL

Strong mayoral authority is essential.

## 9.1 Executive Directive

Mayor must issue formal directive:

- MESOB Phase 1 services are mandatory digital channels

- All bureaus must comply

- SLA compliance required

- Data-sharing mandatory

## 9.2 Compliance Audit

Quarterly audit must verify:

- API functionality

- SLA compliance

- Data integrity

- Payment reconciliation

- Security logs

## 9.3 Corrective Action Framework

If bureau fails to comply:

Step 1: Warning
Step 2: Performance review
Step 3: Escalation to Executive Steering Committee
Step 4: Administrative action

# CATEGORY B SUMMARY

If bureau has no IT system:

Primary focus = Backend creation + API exposure.

Integration complexity = High.

Risk = Institutional resistance + technical delays.

Mitigation = Clear vendor scope + mayoral enforcement.

# DOCUMENT 5 COMPLETE

This concludes:

✔ Stakeholder mapping
✔ Governance structure
✔ Category A readiness framework
✔ Category B transformation model
✔ API responsibility model
✔ Capacity building plan
✔ Enforcement & compliance strategy

Reply with:

“Proceed with Document 6, Part 1.”

Next we begin:

Core Technology Architecture
(API endpoints, data exchange mesh, localized data center requirements, and enterprise architecture diagram logic).