Excellent.

We now produce:

# DOCUMENT–3

# Comprehensive Infrastructure & Technology Plan

### (Service-Driven, Risk-Preventive Technical Framework)

### Installment 1 of 2

# SECTION I

# Service Integration Architecture & Capacity Modeling

## 1. Purpose of This Technical Plan

This document translates Hawassa City’s aggressive but structured service integration strategy into a technically dimensioned, scalable, and secure infrastructure architecture.

Unlike traditional infrastructure documents that begin with hardware specifications, this plan begins with service volume, service complexity, and integration pace, because infrastructure must be engineered to serve demand — not estimated blindly.

Benchmarking has shown that rapid integration is possible (17+ organizations and 70+ services within 6 months). However, rapid integration without capacity modeling risks:

- Server overload

- Network congestion

- Under-provisioned counters

- Security compromise

- Infrastructure redundancy gaps

This plan ensures Hawassa integrates faster — but safer, dimensioned, and scalable.

# SECTION II

# Comprehensive Service Inventory & Integration Scope

## 2. Service Domains to be Integrated

Based on our 9-part MESOB framework and current institutional mapping, Hawassa City MESOB will integrate services under the following structured domains:

### 2.1 Administrative & Civil Services

- Civil registration services

- Identification verification

- Certification issuance

- Residency confirmation

- Official document authentication

### 2.2 Land & Urban Development Services

- Land holding confirmation

- Land transfer requests

- Plot allocation

- Lease processing

- Urban planning approvals

### 2.3 Construction & Permit Services

- Building permit issuance

- Plan approval

- Construction compliance review

- Occupancy certification

- Site inspection scheduling

### 2.4 Revenue & Tax Services

- Tax registration

- Tax clearance certificates

- Business tax payment

- Property tax processing

- Revenue compliance certification

### 2.5 Trade & Licensing Services

- Business license issuance

- License renewal

- Sector-specific licensing

- Trade registration

- Trade amendment requests

### 2.6 Justice-Related Services

- Legal document verification

- Public notary services

- Certification requests

- Case status documentation

### 2.7 Investment Services

- Investment permit facilitation

- Investor documentation processing

- Industrial coordination services

### 2.8 Public Utility Integration

- Water account services

- Electricity account services

- Utility connection requests

- Utility payment validation

### 2.9 Sub-City & Decentralized Services

- Local administrative clearances

- Community-level approvals

- Sub-city certification services

### 2.10 National Digital ID (Fayda) Integration

- On-site registration

- Identity verification

- Cross-service authentication

# SECTION III

# Service Volume & Capacity Modeling

To engineer infrastructure responsibly, we model projected load scenarios.

## 3.1 Integration Pace Assumptions

We propose:

Year 1:

- 15–20 bureaus

- 80–120 services

- High-volume services prioritized

Year 2:

- 120–160 services

- Inter-bureau workflow integration

- Increased automation

Year 3:

- Hybrid physical + online service expansion

## 3.2 Daily Traffic Modeling

Based on urban population scale and economic activity:

### Scenario A — Conservative Model

- 600 users/day

- Average transaction time: 15–20 minutes

- 25–30 counters required

### Scenario B — Moderate Model

- 1,200 users/day

- 35–45 counters required

- 30–40 concurrent database sessions

### Scenario C — Aggressive Integration Model

- 2,000–2,500 users/day

- 50–60 counters required

- 60–80 concurrent sessions

- 3x peak-hour load (morning spike)

Infrastructure must be dimensioned at least for Scenario B, with scalability to Scenario C without major redesign.

## 3.3 Peak Load Considerations

Peak window assumption:

- 9:00 AM – 12:00 PM

- 40% of daily traffic concentrated

System must handle:

- High simultaneous login sessions

- Rapid QMS ticket issuance

- API verification spikes

- National ID verification load

# SECTION IV

# Service Identification & Digital Readiness Capacity Building

Service integration failure often begins with poor service definition.

## 4.1 Service Identification Standardization

Each service must define:

- Service name

- Required input documents

- Data fields required

- Processing steps

- Decision authority

- Estimated processing time

- Output format (certificate, approval, license)

Without this clarity:

- API development stalls

- Data mapping fails

- Automation becomes inconsistent

## 4.2 Capacity Building Program

Before aggressive integration:

- Service Identification Workshop (per bureau)

- Data Standardization Training

- API Readiness Training

- Documentation Digitization Support

This ensures infrastructure utilization is effective, not idle.

# SECTION V

# Data Center Architecture (Dimensioned for Aggressive Integration)

## 5.1 Data Center Design Objectives

The data center must support:

- Minimum 1,200 concurrent daily users

- Scalable growth to 2,500 users/day

- High availability architecture

- Secure API exposure

## 5.2 Server Architecture

### Core Components

- Application Server Cluster (Virtualized)

  - Load-balanced configuration

  - Minimum 2-node cluster

- Database Server

  - High-performance storage

  - RAID 10 configuration

  - Redundant disk array

- Backup Server

  - Daily incremental backup

  - Weekly full backup

- Storage System

  - Initial sizing: 10–15 TB

  - Scalable expansion capacity

## 5.3 Virtualization Strategy

- Hypervisor-based infrastructure

- Resource allocation per bureau

- Isolation for security segmentation

- Rapid provisioning capability

## 5.4 Environmental Controls

- Dedicated cooling system

- Temperature threshold monitoring

- Humidity control

- Overheat alert system

# SECTION VI

# Redundancy & Disaster Recovery Framework

## 6.1 Power Redundancy

- Generator capacity sufficient for full operational load

- UPS battery backup minimum 30–45 minutes runtime

- Automatic transfer switch

## 6.2 Data Redundancy

- Real-time database replication (if feasible)

- Scheduled backup rotation

- Off-site encrypted backup storage (long-term)

## 6.3 Disaster Recovery Objectives

- RTO (Recovery Time Objective): < 4 hours

- RPO (Recovery Point Objective): < 30 minutes

- Annual failover simulation mandatory

# SECTION VII

# Network Architecture

## 7.1 Core Network Layout

- Core Layer Switch

- Distribution Switches

- Access Switches per counter block

- VLAN segmentation per bureau

## 7.2 VPN Architecture

- Secure VPN for bureau integration

- Encrypted communication channels

- Segmented API access

## 7.3 Internet Bandwidth Strategy

Minimum baseline:

- 100 Mbps dedicated line

Scalable to:

- 200–300 Mbps under Scenario C

Traffic prioritization:

- API calls

- Database traffic

- QMS real-time updates

# SECTION VIII

# Firewall & Security Architecture

## 8.1 Perimeter Firewall

- Enterprise-grade firewall

- Intrusion prevention

- Application-layer filtering

## 8.2 Credential Governance

- Firewall credentials owned by MESOB IT Division

- Vendor access temporary and logged

- Dual authentication for configuration changes

## 8.3 Monitoring & Logging

- Centralized log server

- Real-time alerting

- Incident response protocol

# INSTALLMENT 1 CONCLUSION

Installment 1 has established:

- Full service inventory structure

- Aggressive integration modeling

- Capacity-based infrastructure sizing

- Data center architecture

- Network and security framework

- Disaster recovery standards

- Service identification capacity-building linkage

Installment 2 will cover:

- Counter terminals & hardware standards

- Self-service kiosks

- QMS & Business Intelligence integration

- Biometric attendance systems

- Power distribution engineering

- Installation sequencing protocol

- SLA enforcement framework

- Maintenance & monitoring model

- IT staffing model

Shall we proceed to Installment 2?

Excellent.

We now proceed with:

# DOCUMENT–3

# Comprehensive Infrastructure & Technology Plan

### (Service-Driven, Risk-Preventive Technical Framework)

### Installment 2 of 2

# SECTION IX

# Endpoint & Service Delivery Hardware Architecture

Infrastructure capacity is meaningless without properly engineered service delivery endpoints. This section defines the physical interface between citizens and the digital backbone.

## 9. Counter Terminal Standards

Each service counter must be uniformly engineered to avoid performance inconsistency.

### 9.1 Workstation Specifications

Minimum baseline configuration (dimensioned for Scenario B with scalability):

- Enterprise-grade desktop workstation

- Minimum 16GB RAM (scalable to 32GB)

- SSD storage (minimum 512GB)

- Gigabit network interface

- Dual-monitor configuration (service efficiency optimization)

### 9.2 Peripheral Requirements

Each counter must include:

- High-speed document scanner

- Laser printer (shared per cluster where feasible)

- Smart card reader (National ID integration)

- Biometric fingerprint reader (where applicable)

- Webcam for digital documentation capture

- UPS socket protection per workstation

### 9.3 Counter Quantity Planning

Dimensioning by traffic model:

| Scenario | Estimated Counters |
| --- | --- |
| Conservative (600/day) | 25–30 |
| Moderate (1,200/day) | 35–45 |
| Aggressive (2,000+/day) | 50–60 |

Infrastructure must support up to 60 counters without redesign.

# SECTION X

# Self-Service Kiosk Architecture

Self-service kiosks reduce pressure on human counters and prepare for long-term digital migration.

## 10.1 Kiosk Functional Scope

- Ticket issuance (QMS integration)

- Service pre-registration

- Document upload

- National ID verification

- Status tracking

- Basic information access

## 10.2 Technical Specifications

- Industrial-grade touchscreen

- Hardened OS

- Encrypted communication

- Built-in camera

- Smart card reader

- Accessibility compliance

## 10.3 Deployment Model

Initial phase:

- 3–5 kiosks

Expansion-ready design:

- Space and network provisioning for 10+ kiosks

# SECTION XI

# Queue Management System (QMS) & Business Intelligence

## 11.1 QMS Core Components

- Ticket dispenser unit

- Central QMS server integration

- Overhead display screens

- Counter display panels

- Audio call system

## 11.2 Business Intelligence (BI) Dashboard

The QMS must integrate with BI to provide:

- Service time analytics

- Bureau performance comparisons

- Peak hour analysis

- Staff efficiency tracking

- Daily service count reporting

Dashboard must be accessible to:

- MESOB Director

- City Executive (summary view)

- Integration Unit

# SECTION XII

# Biometric Attendance & Access Control (ZKTeco-Based Model)

Biometric systems ensure staff accountability and physical security.

## 12.1 Staff Attendance System

- Biometric terminal at staff entrance

- Integrated attendance reporting

- Linked with HR performance system

## 12.2 Data Center Access Control

- Biometric + access card dual authentication

- Access logging

- Audit trail storage

## 12.3 Integration Requirements

- Network-isolated from public counters

- Secure database logging

- Monthly audit export

# SECTION XIII

# Power Engineering & Electrical Load Management

## 13.1 Generator Capacity Planning

Generator must sustain:

- Full counter operation

- Data center

- Network equipment

- Cooling system

- Lighting

- Security systems

Capacity sizing must assume 100% load under Scenario C.

## 13.2 UPS System Design

UPS must:

- Provide 30–45 minute runtime for full load

- Cover data center and core network first priority

- Protect counter clusters in prioritized order

Battery health testing:

- Quarterly inspection

- Annual replacement cycle planning

## 13.3 Electrical Distribution

- Dedicated power lines for data center

- Surge protection units

- Grounding compliance

- Load balancing across phases

# SECTION XIV

# Installation Sequencing & Acceptance Protocol

To avoid installation mismatches:

## 14.1 Pre-Installation Checklist

- Civil works fully complete

- Ceiling cable trays installed

- Rack room insulation verified

- Power lines tested

## 14.2 Installation Order

- Power infrastructure

- Rack mounting

- Core switches

- Firewall

- Servers

- Backup system

- Counter endpoints

- QMS devices

- Kiosks

- Biometric devices

## 14.3 Acceptance Testing

Before operational declaration:

- Network stress test

- Peak-load simulation

- Failover simulation

- Backup restoration test

- Security penetration testing (basic internal)

Operational declaration only after documented validation.

# SECTION XV

# SLA Enforcement Framework

Vendor agreements must include enforceable clauses.

## 15.1 Installation Milestone Structure

Payment linked to:

- Hardware delivery

- Installation completion

- Testing validation

- Operational readiness certification

## 15.2 Downtime Penalty Clause

Defined maximum downtime per month.

Escalation ladder:

- 1 hour response (critical)

- 4 hour resolution target

- Financial penalty beyond threshold

## 15.3 Technician Availability Clause

- Dedicated technical contact

- Escalation manager

- Spare parts inventory guarantee

# SECTION XVI

# Maintenance & Monitoring Model

## 16.1 Preventive Maintenance Calendar

Monthly:

- Firewall review

- Server health check

- Log audit

Quarterly:

- UPS battery check

- Generator testing

- Network load audit

Annually:

- Full DR simulation

- Security audit

- Hardware lifecycle assessment

## 16.2 Infrastructure Monitoring Dashboard

Central dashboard displaying:

- CPU load

- Memory utilization

- Network throughput

- Disk health

- Security alerts

- Backup status

Automated alert escalation to IT team.

# SECTION XVII

# IT Staffing Model

To sustain aggressive integration:

## 17.1 Required Roles

- IT Manager

- Network Engineer

- System Administrator

- 2 Cybersecurity Specialists

- Helpdesk Support Officers (2–3)

- Integration Coordinator

## 17.2 Capacity Scaling Plan

As service volume grows:

- Additional helpdesk staff

- Data analyst for BI optimization

- API integration specialist (in collaboration with HU)

# SECTION XVIII

# Expansion Philosophy & 5-Year Technical Vision

Aggressive integration does not mean reckless expansion.

### Year 1:

- Physical integration backbone established.

- 80–120 services operational.

### Year 2:

- Service expansion and performance optimization.

- 150+ services possible.

### Year 3:

- Hybrid physical + online processing.

- Partial remote application capability.

### Year 4–5:

- Full digital-first architecture.

- MESOB becomes integration and oversight hub rather than high-volume physical center.

Infrastructure selected today must support this evolution without replacement.

# FINAL TECHNICAL DECLARATION

This Comprehensive Infrastructure & Technology Plan ensures:

- Service-driven infrastructure dimensioning.

- Scalable architecture.

- Security-by-design implementation.

- Redundancy from inception.

- SLA-based vendor accountability.

- Integration readiness for aggressive service expansion.

- Transition capability toward digital governance.

Document–3 Complete.

We are now ready to move to:

Planning Blueprint for Document–4: Complete Quick-Impact Action Plan (30–60–90 Day Acceleration Framework).

Shall we proceed?