Excellent.

We now proceed with full structural alignment to:

- Document–1 → Strategic Political & Governance Justification

- Document–2 → Institutional & Organizational Model

- Document–3 → Technical Infrastructure & Capacity Plan

Everything below is engineered to remain fully consistent with those three documents.

# DOCUMENT–4

# 30–60–90 Day Quick-Impact Acceleration Framework

### (Execution Plan for Hawassa City MESOB Operational Launch)

# SECTION I

# Purpose of This Document

If:

- Document–1 justified why MESOB must exist,

- Document–2 defined who governs and manages it,

- Document–3 engineered the technical backbone,

Then:

Document–4 defines how we move from approval to operational reality — without delay, confusion, or political friction.

This is a controlled acceleration model — not rushed implementation.

# SECTION II

# Guiding Principles for Execution

To avoid inconsistency with previous documents, the 30–60–90 model is built on five core constraints:

- Infrastructure must match service volume modeling (Document–3).

- Bureau integration must respect institutional authority (Document–2).

- Political messaging must remain consistent with governance positioning (Document–1).

- Integration must be aggressive but administratively structured.

- No service goes live without process mapping and data standardization.

# SECTION III

# PHASE 1 (Days 1–30)

# Institutional Lock-In & Technical Mobilization

## 3.1 Political & Administrative Formalization

Deliverables:

- Mayor’s formal directive establishing MESOB Integration Mandate.

- Cabinet endorsement of service migration framework.

- Official communication to all bureaus confirming phased integration schedule.

Purpose:
Prevent resistance ambiguity.

Consistency Check:
Aligned with Document–2 authority model (MESOB under City Administration).

## 3.2 Service Identification Sprint

Each priority bureau must submit:

- Service inventory

- Service volume estimates

- Required documents

- Processing steps

- Approval hierarchy

- Estimated transaction time

Target:
10–12 bureaus fully mapped within 30 days.

Output:
Service Architecture Matrix (feeds directly into infrastructure provisioning from Document–3).

## 3.3 Building & Civil Readiness

Parallel activities:

- Final space allocation for:

  - Data center room

  - Counter hall

  - QMS area

  - Kiosk zone

  - Executive monitoring room

- Electrical wiring preparation

- Rack room insulation

- Cable tray installation

Constraint:
No hardware delivery before civil readiness sign-off.

## 3.4 Vendor Technical Kickoff (Ethio Telecom Alignment)

- Confirm BoQ itemization matches Document–3 architecture.

- Confirm firewall credential ownership model.

- Confirm SLA enforcement structure.

- Establish installation sequencing calendar.

No deviation from approved architecture without Executive Committee sign-off.

# SECTION IV

# PHASE 2 (Days 31–60)

# Infrastructure Installation & Controlled Bureau Onboarding

## 4.1 Data Center Deployment

Installation sequence:

- Power systems (UPS + generator sync)

- Server racks

- Core switches

- Firewall

- Virtualization environment

- Backup configuration

- Monitoring dashboard activation

Acceptance testing must include:

- Peak simulation

- Failover test

- Backup restoration test

Only after validation can application onboarding begin.

## 4.2 Counter Infrastructure Deployment

- 30–40 counters initially activated (Scenario B baseline).

- QMS hardware installation.

- Counter device provisioning.

- Biometric staff registration.

No bureau allowed to move in without:

- Digitized service template.

- Trained personnel.

- Integration checklist completion.

## 4.3 First-Wave Bureau Integration (Controlled Launch)

Target:
5–8 high-impact bureaus in first operational wave.

Selection Criteria:

- High citizen volume.

- Process clarity.

- Political visibility.

- Revenue impact.

Examples:

- Trade & Licensing

- Revenue Office

- Land Confirmation Services

- Construction Permit Intake

Soft Launch Model:
First 10 operational days limited capacity.
Performance monitoring daily.

# SECTION V

# PHASE 3 (Days 61–90)

# Public Launch & Expansion Stabilization

## 5.1 Public Communication Strategy

Aligned with Document–1 political framing:

Messaging themes:

- Efficiency

- Transparency

- Reduced corruption opportunities

- Faster service

- One-stop convenience

Avoid:
Overpromising digital transformation in first 90 days.

## 5.2 Second-Wave Bureau Integration

Additional 7–10 bureaus onboarded.

By Day 90:

- 15–20 bureaus operational.

- 80–120 services active.

- Fully consistent with Document–3 Year 1 modeling.

## 5.3 Performance Dashboard Activation

Executive Dashboard must show:

- Daily service count

- Average waiting time

- Peak hour pattern

- Bureau performance comparison

- System uptime

Mayor receives weekly executive summary.

## 5.4 Resistance Mitigation Protocol

From Document–2 risk modeling:

Resistance categories:

- Bureau autonomy anxiety

- Revenue control concerns

- Staff relocation discomfort

- Fear of transparency

Mitigation tools:

- Integration coordination meetings

- Clear revenue tracking model

- Public success metrics

- Leadership endorsement visibility

# SECTION VI

# 90-Day Milestone Targets

By Day 90, the following must be true:

- Data center operational and monitored.

- 30–40 counters fully active.

- 15+ bureaus integrated.

- QMS analytics functioning.

- Disaster recovery tested once.

- Public confidence established.

Failure to meet any of the above triggers internal corrective review.

# SECTION VII

# Resource Synchronization With Document–3

This 90-day plan assumes:

- Infrastructure dimensioned for Scenario B.

- Staff recruitment timeline initiated in parallel.

- Training programs operational by Day 45.

- SLA enforcement active from installation start.

No structural contradictions exist between this execution plan and previously approved technical framework.

# SECTION VIII

# Risk Map (Cross-Document Alignment)

| Risk | Covered in Doc | Mitigation Phase |
| --- | --- | --- |
| Infrastructure overload | Doc–3 | Phase 2 validation |
| Bureau resistance | Doc–2 | Phase 1 & 3 engagement |
| Political misalignment | Doc–1 | Phase 1 directive |
| Service misdefinition | Doc–3 | Phase 1 service sprint |
| Vendor delay | Doc–3 SLA | Phase 1 contract enforcement |

# SECTION IX

# Transition to Document–5

After 90 days:

Focus shifts to:

- Full-year stabilization.

- Financial sustainability model.

- Institutional legal codification.

- Performance benchmarking.

- Citizen satisfaction analytics.

This will be addressed in:

Document–5: Operational Sustainability & Governance Codification Framework

Document–4 Complete.

Shall we proceed to Document–5?