A 24-month roadmap for smart city implementation, specifically defined by the "Hawassa Model," entails a disciplined, three-phase approach designed to build institutional momentum, secure public trust through "Quick Wins," and establish a robust foundation for data-driven governance. This strategy explicitly rejects a high-risk "big bang" implementation in favor of focused, scalable growth.

### Phase I: Foundational Core & Quick Wins (Months 1–9)

The strategic objective of this phase is to establish the technical and governing architecture of the partnership while delivering immediate, tangible value to citizens.

- Partnership Mobilization (Months 1–2): This includes formalizing the Transformation Management Office (TMO), establishing the Joint Steering Committee (JSC), and forming Joint Technical Working Groups (JTWGs) for each service module.

- Deep Discovery & Architectural Design (Months 1–4): Intensive workshops are conducted to map and re-engineer internal processes. The technical architecture—including the secure API layer, the central data warehouse structure, and the cybersecurity plan—is designed and approved by the JSC.

- The "Quick, Visible Win" (Months 3–6): To build public trust, the partnership launches the Online Business License Renewal Portal. This addresses a major annual pain point for thousands of business owners, providing a high-impact demonstration of the system’s value.

- Core System Development & Deployment (Months 4–9): Launch of the first foundational systems from the Smart Governance pillar: the Digital Revenue & Finance System and the Integrated Investment & Business Licensing System.

### Phase II: Service Expansion & Full Integration (Months 10–24)

This phase focuses on building out the full suite of prioritized services and achieving a seamlessly integrated digital platform that eliminates data silos.

- Development of Priority Pillar Systems (Months 10–18): Launch of systems that define the city's unique identity, such as the "Visit Hawassa" Digital Tourism Portal and the "Health of the Lake" real-time monitoring system.

- Foundational Expansion (Months 16–24): Development of the Digital Cadaster and Land Management System, along with initial modules for Smart Mobility (e.g., Smart Parking) and Smart Security (e.g., the Public Alert System).

- Platform Integration & Training: All launched modules are integrated through the secure API layer to ensure automated data flow between departments. Simultaneously, the TMO conducts a city-wide "Train-the-Trainer" program to build deep internal capacity.

### Phase III: Data Intelligence & Long-Term Stewardship (Month 20 Onwards)

The final phase transitions the initiative from a collection of digital services to a unified platform for evidence-based governance.

- Data Warehouse Operationalization: The Smart City Data Warehouse is populated with anonymized, structured data from all service modules.

- Leadership Dashboard Deployment (Month 24): Launch of the Smart City Executive Dashboard, allowing city leadership to monitor Key Performance Indicators (KPIs) in real-time.

- Analytics Pilot Projects: Initiation of at least two pilot projects utilizing Artificial Intelligence (AI) and Machine Learning (ML) for predictive analytics (e.g., traffic hotspots or revenue anomalies).

- Stewardship Framework: Finalization of a long-term Service Level Agreement (SLA) to govern the partnership and system maintenance beyond the initial 24-month roadmap.

### Governing Principles of the Roadmap

- Digital Sovereignty: The city retains 100% ownership of all source code, data, and systems, preventing "vendor lock-in."

- Fayda ID Integration: Every service is anchored to the National Digital ID for secure authentication and a "single source of truth."

- Transformation-Focused Change Management: The TMO manages the "human side" of the change, ensuring civil servants are not just trained but empowered to use the new workflows.

- Audit-Proof Accountability: Payments are strictly milestone-based, meaning the city only pays after its own experts have formally tested and accepted the results of each development sprint.