- Gaaaps

  - Resistance to adopt and start by some bureaus

  - Civil work, technology all in one month

  - Delay in service start

  - There was high attention given by regional leaders

  - Construction side gaps

    - No experience

    - Quality absence yet lots of money

  - Technology

    - Ethio-telecom, technology in

      - accessories not provided at need time

      - Wi-Fi initially planned for throughout, but then celling was bore cable installation at wrong time. This do to ddelayss

    - irewall over yesterday

  - physica installation problem

    - ystem side no problem

    - tele side

  - Cost wise other comapy thnan tee

  - Time of payment is flexible but too expensive

  - SHangay company

  - Tele very positive, no transactional corruption ear cause it is gov org, balemuya itret with Tele

  - Imat, construc memriya, fitih memriya, gebiwoch – including kifle ketemoch. Fitih is very much doing well ots of customer

  - Not started yet: contruction memriya

    - People very resistant:

      - Not interested for some reason after 4 5 meetings

    - Meret limat

  - They (serve customers) do it manually there not willing to send them here to Mesob

- Prioritization

  - Services with lots of customers

- Public Service reform

  - No many bureau has system, they use federal system (HU Can Help here)

  - Identification

  - HU with Public Service can help**********

- Mainly done by AI Federal Institute, we only did installation based on their specification, then API integration

- Service charge, not started yet but waiting on and planning

- National ID, they register here it self if they don’t have.

  - ..

  - ..PROMOT, LINKUP

- 17 tekuam, 72 services (neusan agelgilot). Potential 21 tekuamat

- Mebrat, wuha, INduatry Park (they already have similar thing, instead of brining business owners here let that system improve to Mesob there itself)

- Tele-Package

  - Platinium

- How many customers per service expected??

- Infrustructure (fully Tele), Software Part (AI Institution), we localized as support AI Institute (e.g. Sidama Translation),

  - 9 Standard Software

  - System Maturity Check of Systems (of What), then AI comes and confirms, API6 integration.

    - Maturity check – Innovation and Technoloy

    - NW, technology etc must be, infrastructure, electronics

- Land and Construction: only 3 land, construction 5, no services yet (3 counters ) but not giving services, Service Mapping has been done but they don’t want to come and use

  - Land, Investimate, Contruction etc HIGH RESISTANT

- Nigd: came from kifle ketema, memiriya almetam, why?/

  - Counter why they should be empty

  - Only one service still

- Federal Mesob is Good

- HU – maturity check etc check

  - NEED Assessment is must

  - Asgedaj endimetu madreg

  - Consult, infrastructure

- Public service

- BUG Issues

- Mini data center –

  - Generator, UPS not available

- Power, (elpa – 2 side, generator, UPS)

- Connetivity: VPN, Internet

  - VPN – Mesob VPN

  - 100MBS speed

    - Corridor limat gemed mekorrart

    - What is make 2 VPN to fix this

  - Speed is very good no issue, it is all based on standard

- All service time and service mapping has been done and on portal

- 600 users max, QMS working with Business Inteligence System nicely

- No tele cloud, Federal said standard is your own servers

- If services are invited, 2000+ per day or even more can be served cause no VPN or Internet issues

- Regional Data Center (7 cities coming to Mesob in Sidama so cant ask them for their own data center, so Region helping here, deision in 2 days hopeful)

- Complaint handling system, System security team, Maintenance readiness and identification. Is it done by employee’s here or not? Anti corruption, gender, etc.

  - How to manage Mesob is not planned, structure, organization etc

- Window: how many time they spent on the system, based on maturity, and Training are offered. But enat-mesriya bet may give IT oeole or others

- Firewall credentials etc with tele (initially cloud planned but then local so removed cloud and replace by Firewall purchase). When security employee come, we might take the credentials.