This is a critical juncture for the Hawassa Mesob Center. Based on a deep review of your internal operational blueprints (the 47 priority Phase 1 services), the Ethio Telecom BoQ, and the comparative Sidama Regional contracts, it is clear that Ethio Telecom has proposed a "Maximum Capacity/Final Phase" hardware package.

Hawassa’s actual need right now is a "Minimum Viable, High-Impact Launch" to get 47 services running efficiently without draining the municipal budget on premature infrastructure.

To ensure the Mayor and the Steering Committee have a clear, defensible, and constructive path forward, I propose structuring our strategic advisory output into four distinct, connected deliverables:

### Proposed Deliverable Structure

- Deliverable 1: The Mayor’s Executive Briefing (The Strategic Stance)

  - What it is: A high-level, 2-page synthesis outlining the current situation, the financial and operational stakes, and the recommended strategic posture.

  - Why it matters: Leadership needs a simple narrative. We reframe Ethio Telecom’s BoQ not as a "bad proposal," but as an "over-dimensioned Phase 2 vision" that must be right-sized for our Phase 1 reality.

- Deliverable 2: The Phase 1 "Minimum Viable Launch" Matrix

  - What it is: A pragmatic categorization of the BoQ into three buckets: Core/Essential (procure from Ethio Telecom now), Alternative Sourcing (procure locally/internally for better ROI), and Deferrable/Phase 2 (unnecessary for the immediate 47 services).

  - Why it matters: It gives the technical and finance teams a defensible framework to cut costs logically, tied directly to the 47 approved services.

- Deliverable 3: The Cross-Regional Insight (Hawassa vs. Sidama)

  - What it is: A brief comparative analysis showing what Sidama bought (heavy hardware/displays) versus what Hawassa should buy (software-driven, lean edge computing).

  - Why it matters: It protects the Mayor politically by showing that Hawassa is learning from regional precedents and innovating, not just copying expensive models.

- Deliverable 4: The Constructive Negotiation Playbook

  - What it is: A set of calm, evidence-backed questions and counter-proposals for Ethio Telecom.

  - Why it matters: It maintains Ethio Telecom as a vital strategic partner while firmly protecting Hawassa’s budget (e.g., resolving the EAII HRMS overlap, clarifying Wi-Fi 7/smart screen specs, and unpacking the "accessories" bundle).

### STEP 1: Executing Deliverable 1

To build immediate momentum, here is the draft of the Mayor-Level Executive Briefing.

## STRATEGIC EXECUTIVE BRIEFING: Hawassa Mesob Center Infrastructure

To: H.E. Mayor, Hawassa City Administration

Subject: Strategic Assessment of Ethio Telecom BoQ & Phase 1 Launch Strategy

1. THE SITUATION

Hawassa City is preparing to launch the Phase 1 Mesob Center, prioritizing 47 critical citizen services (Land, Revenue, Trade, Health, etc.). To support this, Ethio Telecom has submitted a comprehensive infrastructure Bill of Quantities (BoQ).

Simultaneously, we have reviewed the Sidama Region’s Mesob deployment to extract lessons learned. Ethio Telecom is a vital national partner, and their core network connectivity is essential to our success. However, their submitted BoQ represents a "Maximum Capacity" enterprise setup, anticipating years of future growth.

2. THE STRATEGIC DILEMMA

If we accept the BoQ as submitted, we risk locking municipal funds into heavy, expensive hardware (massive video walls, over-engineered endpoints, and redundant software) that is not strictly required to launch our 47 core services today.

Our guiding principle must be "Service-Driven Dimensioning." We must invest heavily in what directly impacts the citizen experience (stable core network, efficient queuing, reliable data) and defer aesthetic or heavy-enterprise infrastructure until service volume demands it.

3. KEY COST PRESSURE POINTS & MISALIGNMENTS

A preliminary review has identified several areas where the proposal misaligns with our immediate Phase 1 needs:

- Software Redundancy: The BoQ includes an expensive "Attendance & Time Management System." The Ethiopian AI Institute (EAII) already provides a comprehensive HRMS. Procuring this from Ethio Telecom is a redundant expenditure.

- Premature Visual Infrastructure: The proposal includes multiple layers of display tech (a massive LED wall and a Situation Room Video Wall and comprehensive 65" LCDs). Phase 1 only requires functional queue-management displays.

- Over-Specified Endpoints: The inclusion of premium equipment (e.g., Wi-Fi 7 access points, Core i7 laptops) is highly excessive for running browser-based e-governance portals.

- Opaque "Bundled" Costs: Significant funds are allocated to vague "Accessories Packages" and blanket installation fees, which violate standard municipal auditing requirements for line-item transparency.

4. THE REGIONAL CONTEXT (LEARNING FROM SIDAMA)

Sidama’s deployment heavily prioritized physical IT infrastructure (e.g., highly expensive customized LED structures and premium endpoint hardware). Hawassa has the opportunity to optimize this model. By focusing on a "Lean Edge" architecture—where core network stability is prioritized over expensive localized hardware—Hawassa can launch faster, at a lower cost, and with higher software efficiency.

5. RECOMMENDED PATH FORWARD

We do not recommend rejecting Ethio Telecom’s proposal. Instead, we recommend a Phased Procurement Strategy:

- Re-Categorize the BoQ: We will divide the proposal into "Phase 1 Essentials" (core network, routing, SLA management) and "Phase 2 Expansions" (video walls, hyper-scale UPS).

- Unbundle Endpoints: We strongly advise separating the procurement of endpoint hardware (laptops, basic monitors, standard furniture) from the telecom contract. Procuring these locally via standard municipal supply chains will yield massive savings.

- Initiate Constructive Dialogue: We will present Ethio Telecom with our Phase 1 requirements (supporting exactly 47 services) and ask them to right-size their proposal to match our immediate operational reality, clarifying overlapping software and premium hardware specs.

Conclusion: By negotiating a "Minimum Viable, High-Impact" launch package with Ethio Telecom, Hawassa will protect its budget, accelerate the launch of the Mesob Center, and set a new national standard for smart, fiscally responsible e-governance.

How would you like to proceed? I can immediately draft Deliverable 2 (The Core vs. Deferrable Matrix) to give your technical team the exact line items to keep, cut, or source locally, OR we can move straight to Deliverable 4 (The Negotiation Playbook) to prep for the vendor meeting.