VOLUME 3: THE "LEAN EDGE" ALTERNATIVE ARCHITECTURE & REDESIGN MANIFESTO

Target Audience: Chief Enterprise Architect, IT Directorate, Mayor’s Office, and Procurement Bureau

Subject: The Engineering & Architectural Redesign of the MESOB Infrastructure (Replacing the 174.3M ETB Turnkey BoQ)

Status: Highly Confidential – Master Engineering Blueprint for Local Sourcing & Vendor Negotiation

### 1.0 ARCHITECTURAL PHILOSOPHY: FROM "HEAVY ENTERPRISE" TO "LEAN EDGE"

#### 1.1 The Fallacy of the "Turnkey Heavy Enterprise" Model

The Ethio Telecom Bill of Quantity (BoQ) is built on a legacy "Heavy Enterprise" architectural philosophy. This model assumes that physical, on-premise hardware must be maximized to ensure performance. It dimensions the facility as if it were a standalone, isolated corporate headquarters running massive local databases and complex rendering workloads.

This philosophy is fundamentally flawed for the Hawassa City MESOB Phase 1 reality. The 47 prioritized services (Land, Revenue, Trade, Health) are not locally hosted monolithic applications. They are distributed, cloud-hosted platforms orchestrated through the Ministry of Innovation and Technology (MInT) and the Ethiopian Artificial Intelligence Institute (EAII).

#### 1.2 The "Lean Edge, API-First" Paradigm

Hawassa City will execute a "Lean Edge" architecture.

In a Lean Edge model, the MESOB facility operates merely as a high-speed, secure gateway to the federal/regional cloud. The computational heavy lifting is done in the data center (Addis Ababa/Hawassa Regional Data Center), not at the counter.

The Core Tenets of Hawassa’s Lean Edge Architecture:

- Dumb Terminals, Smart Cloud: End-user devices at the counter must be low-cost, low-heat, high-reliability web access points (Small Form Factor desktops). We will not pay for unused local processing power.

- Software-Defined, Not Hardware-Locked: Queue management, digital signage, and attendance must run on open APIs, allowing Hawassa University to build custom interfaces without relying on 5.2 Million ETB proprietary kiosks.

- Decoupled Infrastructure: Networking (Layer 1-3) is strictly separated from Commodities (Endpoints, Furniture, Mounts). We will buy connectivity from a telecom, and commodities from hardware distributors.

- Service-Driven Dimensioning: Every piece of hardware must justify its existence against the operational workflow of the 47 Phase 1 services. If it does not actively process a citizen, print a permit, or secure the network, it is eliminated or deferred.

### 2.0 THE RIGHT-SIZED HARDWARE SPECIFICATION CATALOG (LINE-BY-LINE REDESIGN)

This section exhaustively dismantles and redesigns every single line item proposed in the Ethio Telecom BoQ, providing the exact engineering specifications Hawassa City will procure instead.

#### 2.1 Surveillance & Security Hardware

- Original Item 1 & 2: AI Bullet Cameras (4 Pcs) & AI Dome Cameras (13 Pcs)

  - Redesign Logic: Retain. The physical security of a facility handling land deeds and tax revenues is critical. However, they must support ONVIF open standards.

  - Target Lean Spec: Standardize on 5MP IP Cameras. Must guarantee no proprietary software lock-in.

- Original Item 3: PTZ Camera (2 Pcs)

  - Redesign Logic: Retain for exterior perimeter monitoring, subject to unit price validation against standard Hikvision/Dahua rates.

- Original Item 4: 32CH NVR (2 Pcs @ 459,695 ETB each)

  - Redesign Logic: Massively overpriced for pure hardware. A 32-channel Network Video Recorder without enterprise VMS licensing does not cost half a million Birr.

  - Target Lean Spec: Procure 2x Standard Commercial 32CH NVRs via local security vendors. Target price: < 100,000 ETB per unit.

#### 2.2 Visual & Display Systems (Eliminating the Chaos)

- Original Item 5, 6 & 7: Situation Room Video Wall (4x 43" Displays), Support Structures (4 Pcs @ 600K ETB each), Video Wall Decoder (1 Pc @ 1M ETB)

  - Redesign Logic: ELIMINATE ENTIRELY. The BoQ proposes 8.4 Million ETB for a private "Situation Room" viewing wall. Managing the queue for 47 services requires floor managers and tablets, not a cinematic war room. The 600,000 ETB metal brackets are an audit liability.

  - Target Lean Spec: Deferred to Phase 2. Zero Phase 1 CAPEX allocation.

- Original Item 14: Window Display Screen 21" LCD (48 Pcs @ 297,228 ETB each)

  - Redesign Logic: REPLACE. Paying nearly 300,000 ETB for a 21-inch screen implies hidden signage software licenses.

  - Target Lean Spec: Procure 48x standard 21-inch or 24-inch IPS monitors locally. Use HDMI/DisplayPort to connect them as dual-displays to the counter desktops. The desktop browser will run the queue display URL. Target price: < 25,000 ETB per unit.

- Original Item 15: Comprehensive Display Screen 65" LCD (3 Pcs @ 887,617 ETB each)

  - Redesign Logic: ELIMINATE. Visual redundancy. The facility already features an 11.5m2 LED wall. Disjointed 65-inch screens create visual clutter and waste 2.6M ETB.

- Original Item 27, 28, 29, 30, 31: Indoor LED Screen 11.5m2, Controller, Structure, Power Box, Installation Package

  - Redesign Logic: RETAIN WITH MODIFICATION. A centralized LED wall is the correct architectural choice for high-volume citizen queuing. It replaces all other public display needs.

  - Target Lean Spec: Retain the LED hardware, but aggressively negotiate the metal structure (132K/m2 is inflated) and strip the "Installation Package" (177K ETB) if general installation labor is being billed elsewhere.

#### 2.3 Datacenter & Power Infrastructure

- Original Item 8 & 9: 42U Rack (1 Pc) & 22U Rack (3 Pcs)

  - Redesign Logic: UNBUNDLE. Racks are passive metal structures. High-end enterprise networking racks cost a fraction of the quoted ~427K ETB.

  - Target Lean Spec: Procure standard perforated 42U/22U server racks from local ICT wholesalers in Addis Ababa/Hawassa.

- Original Item 10: Centralized UPS 40 KVA (1 Pc @ 11,088,000 ETB)

  - Redesign Logic: REPLACE. An 11 Million ETB valuation for a 40KVA UPS is predatory. Furthermore, under a "Lean Edge" model, the local facility consumes far less power because compute is moved to the cloud.

  - Target Lean Spec: Ensure building has generator auto-failover. Procure 2x 20KVA Enterprise UPS units (APC/Vertiv) configured for N+1 redundancy locally. Target total cost: < 3,000,000 ETB.

#### 2.4 Networking & Connectivity (The Essential Core)

- Original Item 11: Wi-Fi Access Point (6 Pcs @ 451,878 ETB each)

  - Redesign Logic: RETAIN & RE-PRICE. Wi-Fi 6 APs are necessary for the high-density waiting areas. However, the price exceeds global enterprise limits.

  - Target Lean Spec: Retain Ethio Telecom provisioning, but demand the unit price be normalized to standard enterprise distribution pricing (~80K - 120K ETB max).

- Original Item 12: Wi-Fi Access Point Controller (1 Pc @ 1,064,155 ETB)

  - Redesign Logic: ELIMINATE. A dedicated 1M ETB physical hardware appliance to manage 6 Access Points is technologically obsolete architecture from 2010.

  - Target Lean Spec: Mandate a Cloud-Managed controller architecture (e.g., Cisco Meraki, Ubiquiti, Omada) or a virtual machine controller. Cost: 0 ETB (Hardware).

#### 2.5 End-User Compute & Kiosks (The Biggest Waste)

- Original Item 18: Laptop Core i7 (48 Pcs @ 234,782 ETB each)

  - Redesign Logic: REPLACE. Over-engineered. Laptops degrade, batteries fail, Wi-Fi drops, and they are easily stolen.

  - Target Lean Spec: Procure 48x Small Form Factor (SFF) Desktops. Intel Core i3 or i5, 8GB RAM, 256GB SSD. Hardwired via Ethernet for maximum SLA stability. Target Price: ~90,000 ETB. (Saves > 6 Million ETB).

- Original Item 13: Ticket Dispenser Kiosks (2 Pcs @ 5,239,800 ETB each)

  - Redesign Logic: REPLACE. 5.2 Million ETB for a metal box running an Intel Core i3 is an audit disaster.

  - Target Lean Spec: Procure standard capacitive touch Kiosks (Android or basic Windows) locally for < 350,000 ETB each. Software will be handled via API (See Section 3.0).

- Original Item 19: Multi-Function Printer (2 Pcs @ 642,000 ETB each)

  - Redesign Logic: RE-SPECIFY. The BoQ provides zero technical parameters for a 642K ETB machine.

  - Target Lean Spec: Procure Heavy-Duty Enterprise Laser MFPs locally based on exact Pages-Per-Minute (PPM) requirements aligned with the city's paperless targets.

#### 2.6 Audio, Call Center & Civil Overreach

- Original Item 16 & 17: Ceiling Loudspeaker (6 Pcs @ 150K each) & Speaker-Controller-Amplifier (3 Pcs)

  - Redesign Logic: REPLACE. 150K ETB for a passive 6W ceiling speaker is absurd. Buying 3 amplifiers to drive 6 speakers is an architectural error.

  - Target Lean Spec: One standard 100V Public Address Amplifier driving all 6 commercial ceiling speakers. Total cost should not exceed 150,000 ETB for the entire system.

- Original Item 20, 21, 22, 23, 24: Call Center OptiPlex (3 Pcs), Head/Mic, Staff Chairs, Office Tables, Cabinets

  - Redesign Logic: UNBUNDLE. Ethio Telecom is a network provider, not a furniture wholesaler.

  - Target Lean Spec: Extract tables, chairs, and cabinets completely. Procure via Hawassa City standard furniture tenders. Procure Call Center PCs alongside counter SFFs.

- Original Item 34: Contact Center License for 3 Agents (108,000 ETB/yr)

  - Redesign Logic: Retain. This is a legitimate software-as-a-service (SaaS) operational expense for call routing.

#### 2.7 The Opaque "Black Boxes" & Redundant Software

- Original Item 25 & 26: Biometric Device (1 Pc) & Attendance and Time Management System (1 Set @ 2.1M ETB)

  - Redesign Logic: ELIMINATE SOFTWARE. The Ethiopian AI Institute provides government HRMS. Ethio Telecom is selling an off-the-shelf software package that conflicts with our federal integration.

  - Target Lean Spec: Procure the 375K ETB biometric hardware device only if it has an open API. Hawassa University will integrate it (See Section 3.0).

- Original Item 32: Accessories Package (1 Ls @ 11,982,044 ETB)

  - Redesign Logic: SUSPEND & AUDIT. An 11.9 Million ETB blank line item violates procurement law.

  - Target Lean Spec: Zero allocation until a granular Bill of Materials (cables, connectors, faceplates) is provided and audited against market rates.

- Original Item 33: Installation and Commission Service (1 Ls @ 19,770,374 ETB)

  - Redesign Logic: RENEGOTIATE. Double-billing (LED installation is already charged).

  - Target Lean Spec: Recalculate installation as a standard 5-8% margin on the new, right-sized core hardware total, strictly quantified by man-hours.

### 3.0 THE HAWASSA UNIVERSITY "GovTech LAB" INTEGRATION

Hawassa City will not be a passive consumer of expensive, proprietary software modules. The "Lean Edge" architecture relies on the intellectual capital of Hawassa University (HU).

By eliminating the 2.1M ETB Ethio Telecom Attendance System and the proprietary 5.2M ETB Kiosk software locks, we open the ecosystem to the HU GovTech Lab.

The Execution Plan:

- API-First Procurement: Every piece of hardware we procure independently (Kiosks, Biometrics, Queuing displays) must support REST APIs or standard webhooks.

- The Queue Integration: HU computer science graduates will develop a lightweight, web-based queuing portal. The locally procured kiosks will simply run a browser in "Kiosk Mode," pointing to the HU-developed portal. This eliminates 10M ETB in proprietary kiosk hardware costs.

- The Attendance Integration: HU will build the middleware bridge connecting the local Biometric devices directly into the Federal EAII HRMS database, completely bypassing the need for Ethio Telecom’s 2.1M ETB software wrapper.

- Capacity Building: This ensures that when an API breaks or a new service is added in Year 2, Hawassa City has local software engineers who understand the source code, preventing a costly dependency on telecom vendor support tickets.

### 4.0 PHASE 1 VS. PHASE 2 DEPLOYMENT MAPPING

To protect cash flow and ensure operational focus, infrastructure deployment is strictly phased.

#### 4.1 Phase 1: Minimum Viable Service (Months 0–6)

Target: Immediate stabilization of the 47 priority services.

- Core Connectivity: Fiber termination, Edge Routers, Secure Firewalls, and Wi-Fi APs (Ethio Telecom).

- Endpoints: 48x SFF Core i3/i5 Desktops and standard 21" monitors (Locally sourced).

- Public Display: The 11.5m2 LED Wall installed in the main waiting hall for queue visibility.

- Self-Service: Standard Android/PC Touch Kiosks running the HU GovTech web portal.

- Security: Basic NVR and IP camera deployment for internal/external monitoring.

#### 4.2 Phase 2: Scale & Analytics (Months 6–18)

Target: System maturity and advanced data analytics.

- Scale Up Compute: Expand UPS or rack capacity only if the transaction volume of the 47 services maxes out Phase 1 limits.

- The Situation Room: If, and only if, the Mayor requires real-time macro-economic visualizations of city revenue that cannot be viewed on a standard desktop, the dedicated Video Wall will be procured via competitive tender.

- Advanced VMS: Implementation of facial recognition or advanced queue-analytics via the security cameras.

### 5.0 THE TARGET FINANCIAL MODEL: PROVING THE "LEAN EDGE" SAVINGS

By applying this Redesign Manifesto, Hawassa City shifts from a bloated General Contractor model to a laser-focused Core ICT procurement model.

Financial Autopsy of Savings:

- Elimination of End-User Waste: Swapping 48 Core i7 Laptops (11.2M) and proprietary 21" screens (14.2M) for standard SFF desktops and monitors saves ~18 Million ETB.

- Elimination of Kiosk Extortion: Swapping two 5.2M ETB kiosks for local hardware saves ~9.5 Million ETB.

- Elimination of Visual Redundancy: Striking the Situation Room Video Wall, 65" screens, and metal mounts saves ~10 Million ETB.

- Elimination of Power/Network Obsolescence: Replacing the 11M ETB UPS and the 1M ETB Wi-Fi controller with right-sized equivalents saves ~8.5 Million ETB.

- Elimination of Software/Furniture Marks: Removing the Attendance system and office furniture saves ~2.5 Million ETB.

- Auditing the Black Boxes: Forcing the itemization of the Accessories (11.9M) and Labor (19.7M) down to true market rates will conservatively save ~15 Million ETB.

#### The Final Fiscal Reality

- Original Ethio Telecom BoQ: 151,572,868.29 ETB (Subtotal) + 15% VAT = 174,308,798.54 ETB

- Target "Lean Edge" Core ICT Budget (Ethio Telecom Share): ~45,000,000 ETB

- Target Independent Local Procurement Budget (Endpoints/Furniture): ~25,000,000 ETB

- Total Optimized Project Cost: ~70,000,000 ETB to 80,000,000 ETB.

Conclusion of Volume 3

The Lean Edge architecture achieves 100% of the operational requirements for the 47 priority MESOB services while eliminating over 90 Million ETB in vendor margin, proprietary lock-in, and architectural dead-weight. The Steering Committee must mandate this architecture as the non-negotiable technical baseline for all future vendor discussions.

End of Volume 3. Please reply with "Proceed with Volume 4" to generate the Advanced Strategic Interrogation & Rebuttal Framework (The exact branching scripts for the technical and finance committees).

This is the Master Forensic Redesign & Interrogation Table supporting Volume 3.

To ensure impeccable alignment and readability for a massive 16-column matrix, the table is divided by architectural domain. Every single line item from the Ethio Telecom 174.3M ETB BoQ has been forensically extracted, analyzed, and re-engineered according to the "Lean Edge" Phase 1 requirements, complete with exact negotiation scripts and sourcing strategies.

### PART A: DATACENTER, POWER & NETWORKING INFRASTRUCTURE

The core routing, environmental, and connectivity layer. Ethio Telecom’s strongest domain, yet heavily padded with hardware obsolescence and extreme power margins.

| No. | Original Item | Description | Qty | Orig. Unit Price (ETB) | Orig. Total (ETB) | Spec Assessment | Observations | Critical Issues | Alt. Spec (Proposed) | Justification | Cost Reduction | Sourcing | Questions for Vendor | Negotiation Strategy | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | 42U Rack | 64x19 profiles, 800kg load | 1 | 427,670.25 | 427,670.25 | Overpriced | Passive metal framing. | 400%+ markup on passive local infrastructure. | Standard Perforated 42U Server Rack | Metal racks do not require telecom integrations; they are standard commodities. | High (~75%) | Local IT Dist. | "Can Hawassa supply its own 42U rack meeting these exact dimensions?" | Unbundle. Do not buy metal from ISPs. | Procure Independently |
| 9 | 22U Rack | 600x1000 Server Rack | 3 | 202,810.32 | 608,430.96 | Overpriced | Passive metal framing. | High middleman markup. | Standard Perforated 22U Rack | See above. | High (~70%) | Local IT Dist. | "Can we substitute these with locally fabricated/sourced racks?" | Unbundle. | Procure Independently |
| 10 | 40KVA Centralized UPS | 40KVA, Lithium/Lead, SNMP | 1 | 11,088,000.00 | 11,088,000.00 | Hyper-Inflated | Astronomically priced. | Predatory margin (~10x global retail for APC/Vertiv). | 2x 20KVA Enterprise UPS (APC/Vertiv) | Cloud-edge architecture uses less local power. 11M ETB is an audit disaster. | High (~80%) | Local Power Dist. | "Provide the exact Make/Model. Will you price-match an authorized local distributor?" | Threaten to drop from BoQ unless unit price drops below 3M ETB. | Procure Independently |
| 11 | Wi-Fi Access Point | Wi-Fi 6 (802.11ax) Indoor | 6 | 451,878.00 | 2,711,268.00 | Inflated | Nearly $4k USD per AP. | Unjustifiable hardware premium for standard Wi-Fi 6. | Enterprise Cloud-Managed AP (Cisco/Ubiquiti) | Core connectivity is necessary, but standard enterprise APs cost 80k-120k ETB. | Medium (~70%) | Ethio Telecom | "Provide the Cisco/Aruba part number justifying a 451k ETB unit price." | Retain, but force standard distribution pricing. | Modify & Retain |
| 12 | Wi-Fi AP Controller | Hardware Controller | 1 | 1,064,155.80 | 1,064,155.80 | Obsolete | 1M ETB hardware for just 6 APs. | Architectural flaw; pushing unnecessary hardware. | Virtual or Cloud-Managed Controller | Modern AP deployments of this scale utilize cloud/VM controllers (zero hardware cost). | High (100%) | N/A | "Why propose a 1M ETB physical hardware controller for only 6 APs?" | Strike from BoQ entirely. Demand cloud architecture. | Eliminate |

### PART B: END-USER COMPUTE, KIOSKS & COUNTER TECH

The citizen-facing operational layer. This represents the greatest CAPEX waste in the BoQ, prescribing heavy engineering hardware for lightweight browser tasks.

| No. | Original Item | Description | Qty | Orig. Unit Price (ETB) | Orig. Total (ETB) | Spec Assessment | Observations | Critical Issues | Alt. Spec (Proposed) | Justification | Cost Reduction | Sourcing | Questions for Vendor | Negotiation Strategy | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Ticket Dispenser Kiosk | 32" Panel, Intel i3, 4GB RAM | 2 | 5,239,800.00 | 10,479,600.00 | Extortionate | Bottom-tier i3 processor inside a 5.2M box. | Vendor software lock-in; predatory pricing. | Android/PC Touch Kiosk (<350k ETB) | Queuing runs via web APIs. A 5.2M ETB kiosk is an audit violation. | High (~90%) | Local Hardware | "What proprietary tech inside this i3 Kiosk justifies a 5.2 Million ETB price tag?" | Extract hardware. Demand API documentation for HU GovTech integration. | Procure Independently |
| 18 | Laptop Core i7 | Dell Pro14 (16GB/512GB) | 48 | 234,782.61 | 11,269,565.22 | Over-Engineered | Spec is for engineering/CAD. | Severe over-provisioning for web portals; theft risk. | Core i3/i5 Small Form Factor (SFF) Desktops | E-governance is browser-based. SFFs are cheaper, wired, and secure. | Medium (~50%) | Local IT Dist. | "What specific technical workload justifies i7 laptops for browser data entry?" | Strike all laptops. Enforce "Desktop-First" policy locally. | Procure Independently |
| 19 | Multi-Function Printer | General MFP | 2 | 642,000.00 | 1,284,000.00 | Ambiguous | No specs provided. | Hiding margin behind vague descriptions. | Enterprise Laser MFP (Specific PPM) | Cannot approve 642k without duty-cycle and PPM specifications. | Medium (TBD) | Local IT Dist. | "What is the exact Pages-Per-Minute (PPM) and brand of this machine?" | Extract from telecom BoQ; buy via local standard tender. | Procure Independently |
| 20 | Call Center Desktop | Dell OptiPlex i7 | 3 | 200,000.00 | 600,000.00 | Over-Engineered | Call routing does not need i7. | Over-spec. | SFF Core i3 Desktop | Web-based VoIP routing. | Medium (~50%) | Local IT Dist. | "Why i7 processors for VoIP agents?" | Procure with counter PCs. | Procure Independently |
| 21 | Head/Mic | Workstation Headset | 3 | 20,697.63 | 62,092.88 | Justified | Standard pricing. | None. | Standard Call Center Headset | Matches market rate. | Low (0%) | Local IT Dist. | None. | Procure locally to keep endpoints unbundled. | Procure Independently |

### PART C: VISUAL DISPLAY, LED & REDUNDANT SCREENS

Ethio Telecom has proposed three overlapping mass-display systems. Hawassa must eliminate the visual chaos and focus solely on the primary citizen queue board.

| No. | Original Item | Description | Qty | Orig. Unit Price (ETB) | Orig. Total (ETB) | Spec Assessment | Observations | Critical Issues | Alt. Spec (Proposed) | Justification | Cost Reduction | Sourcing | Questions for Vendor | Negotiation Strategy | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Situation Room Video Wall | 43" Displays (2x2) | 4 | 1,250,000.00 | 5,000,000.00 | Redundant | Overlaps with LED Wall. | Visual excess for Phase 1. 1.25M per 43" is inflated. | Eliminate | One public LED wall is sufficient for Day 1 launch. | High (100%) | N/A | "Why is an 8.4M Situation Room necessary alongside a 12.6M LED wall?" | Strike entirely as a deferred Phase 2 luxury. | Eliminate |
| 6 | Video Wall Support Structure | Metal Wall Mounts | 4 | 600,000.00 | 2,400,000.00 | Hyper-Inflated | 600k to hold a 43" TV. | Extortionate pricing on passive metal brackets. | Local Fabrication | Metal is metal. | High (100%) | N/A | "Are you charging 600,000 ETB for a metal VESA mount?" | Strike entirely with Video Wall. | Eliminate |
| 7 | Video Wall Decoder | Decoder Unit | 1 | 1,050,000.00 | 1,050,000.00 | Redundant | Ties to Video Wall. | N/A | Eliminate | Decoder deleted with wall. | High (100%) | N/A | None. | Strike entirely. | Eliminate |
| 14 | Window Display Screen | 21" LCD | 48 | 297,228.81 | 14,266,982.71 | Overpriced | ~300k for a 21" screen. | Likely bundling proprietary signage licenses into hardware. | Standard 21/24" IPS Monitor | Basic monitor connected to SFF desktop browser handles queuing display. | High (~90%) | Local IT Dist. | "Does this include perpetual software licenses, or is this purely hardware?" | Extract and procure standard monitors locally. | Procure Independently |
| 15 | Comprehensive Display | 65" LCD | 3 | 887,617.50 | 2,662,852.50 | Redundant | Clutters waiting area. | Duplicates LED wall function. | Eliminate | Centralize all queuing on the LED board. | High (100%) | N/A | "Why are these needed when we have an 11.5m2 LED board?" | Strike entirely. | Eliminate |
| 27 | LED Screen (Indoor) | Pixel Pitch 1.8 | 11.5 | 1,097,418.00 | 12,620,307.00 | Justified | Core public display. | High CAPEX concentration. | Keep | Replaces all other screens in facility. | Low (0%) | Ethio Telecom | "What is the specific brand of LED modules?" | Retain as the only major visual system. | Retain |
| 28 | LED Controller | 3-in-1 Controller | 1 | 782,717.25 | 782,717.25 | Justified | Core component. | None. | Keep | Required for LED. | Low (0%) | Ethio Telecom | None. | Retain. | Retain |
| 29 | LED Structure | Customized Pole/Frame | 11.5 | 132,335.70 | 1,521,860.55 | Overpriced | Sidama was charged 106k/m2. | 25% markup vs Sidama for passive metal. | Local Fabrication | Sidama benchmark proves inflation. | Medium (~25%) | Local Fab. | "Why is Hawassa paying 132K per m2 when Sidama paid 106K for metal?" | Force price match to Sidama or build locally. | Modify |
| 30 | LED Power Box | Power Distribution | 1 | 538,042.50 | 538,042.50 | Justified | Core component. | None. | Keep | Required for LED. | Low (0%) | Ethio Telecom | None. | Retain. | Retain |

### PART D: SURVEILLANCE, AUDIO, CIVIL WORKS & SOFTWARE

The overlap zone. Ethio Telecom acting as a furniture broker and pushing off-the-shelf software that conflicts with National Federal HRMS mandates.

| No. | Original Item | Description | Qty | Orig. Unit Price (ETB) | Orig. Total (ETB) | Spec Assessment | Observations | Critical Issues | Alt. Spec (Proposed) | Justification | Cost Reduction | Sourcing | Questions for Vendor | Negotiation Strategy | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1-4 | Surveillance Cameras & NVR | AI Bullet/Dome, PTZ, 32CH NVR | 17 | (Varies) | ~1,900,000.00 | Mixed | Cameras OK; NVR heavily inflated (459k/ea). | VMS lock-in risk. | Standard IP ONVIF Cameras + Local NVR | 32CH NVRs cost <100k locally. | Medium (~50%) | Local Security | "Do these cameras require proprietary VMS, or are they ONVIF open-standard?" | Retain cameras if ONVIF. Unbundle NVRs to local sourcing. | Modify & Split |
| 16 | Ceiling Loudspeaker | 6W RMS | 6 | 150,640.00 | 903,840.00 | Inflated | 150k for an analog 6W speaker. | Massive margin on basic PA parts. | Commercial 6W Speaker | Local hardware is identical. | High (~90%) | Local Hardware | "How does Ethio Telecom justify 150,640 ETB for a passive 6W analog speaker?" | Unbundle entirely. | Procure Independently |
| 17 | Speaker-Controller Amp | PA Amplifier | 3 | 492,000.00 | 1,476,000.00 | Arch. Error | 3 Amps for 6 speakers. | 1:2 Ratio is technical nonsense. | 1x Standard PA Amp | 1 Amp easily drives dozens of 6W speakers. | High (~80%) | Local Hardware | "Why are 3 separate amplifiers specified to drive only 6 speakers?" | Unbundle entirely. | Procure Independently |
| 22-24 | Office Furniture | Tables, Chairs, Cabinets | 9 | (Varies) | ~460,000.00 | Misaligned | IT vendor selling MDF wood. | Middleman markup (Sidama paid 52M). | Standard Municipal Furniture | Support local Hawassa furniture economy. | High (~50%) | Local Supply | "We noticed Sidama paid 52M for furniture. We are striking all MDF from this BoQ." | Extract all furniture. Do not allow telecom to act as general contractor. | Eliminate |
| 25 | Biometric Device | Face/Palm/Finger | 1 | 375,000.00 | 375,000.00 | Justified | Necessary hardware. | API lock-in risk. | Open-API Biometric Reader | Must integrate with EAII. | Low (0%) | Ethio/Local | "Does this hardware support open API calls to third-party databases?" | Retain if open API; otherwise source locally. | Retain (Conditionally) |
| 26 | Attendance System | Software & Customization | 1 | 2,100,000.00 | 2,100,000.00 | Redundant | EAII has federal HRMS. | Waste of software licensing fees. | Hawassa Uni (HU) Custom API Bridge | Prevents vendor lock-in. Builds local tech capacity. | High (100%) | Internal (HU) | "Since EAII provides federal HRMS, why are we buying redundant software?" | Strike entirely. Use HU GovTech lab for integration. | Eliminate |

### PART E: THE "BLACK BOXES" (OPAQUE LABOR & ACCESSORIES)

The critical audit failure zones. These lines represent arbitrary, percentage-based profit buffers disguised as integration costs.

| No. | Original Item | Description | Qty | Orig. Unit Price (ETB) | Orig. Total (ETB) | Spec Assessment | Observations | Critical Issues | Alt. Spec (Proposed) | Justification | Cost Reduction | Sourcing | Questions for Vendor | Negotiation Strategy | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 31 | Install Package LED | Cables/Jumpers | 1 | 177,523.50 | 177,523.50 | Double Billing | Installation billed here AND in Line 33. | Double dipping. | Remove | LED labor should be in main installation or base cost. | High (100%) | N/A | "Why are we billed for LED installation here, and again in the 19.7M general line?" | Strike. Force consolidation. | Eliminate |
| 32 | Accessories Package | Unitemized Cables/Mounts | 1 | 11,982,044.92 | 11,982,044.92 | Illegal | 12M ETB blank check. | Violates municipal auditing laws. | Granular Bill of Materials (BoM) | Cannot approve lump sums for "accessories". Sidama was charged 17M. | High (TBD) | N/A | "Provide a line-by-line BoM with unit costs for this 11.9M ETB within 48 hours." | Suspend approval immediately. Refuse to pay without itemization. | Suspend & Audit |
| 33 | Install & Commission | Device Design & Install | 1 | 19,770,374.12 | 19,770,374.12 | Overpriced | ~15% of total hardware cost. | Arbitrary percentage fee, not based on man-hours. | Time & Materials Labor Quote | Cap installation at 5% of the right-sized core network total. | Medium (~60%) | N/A | "Provide a breakdown of this 19.7M by man-hours and engineer hourly rates." | Reject flat percentage. Pay only for actual engineering time. | Modify & Negotiate |